## ES-001
| Note | Analyses | Design | Logistics and ordering | Execution | Test | Feedback | Polishing and Cleaning | Total
Lobby
Design how the lobby will look like |  | 12 | 4 | 1 | 1 | 0.3 | 1 | 0 | 19.3
Change the floor |  | 3 | 0 | 1.5 | 6 | 1.8 | 0 | 0.5 | 12.8
Order new drawers |  | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 4.5
Order a new front door |  | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 4.5
Order a new mirror |  | 4 | 0 | 1.5 | 0 | 0 | 0 | 0 | 5.5
Order hanging cloths rack |  | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 4.5
Change lights |  | 2 | 0 | 1 | 3 | 0.9 | 0 | 0.5 | 7.4
Change the fuses |  | 0 | 0 | 1 | 6 | 1.8 | 0 | 0.5 | 9.3
Upgrade electric installation |  | 0 | 0 | 1 | 6 | 1.8 | 0 | 0.5 | 9.3
Paint the walls |  | 1 | 1 | 4 | 2 | 0.6 | 0 | 0.5 | 9.1
Living room
Design how the living room will look like |  | 24 | 2 | 1 | 1 | 0.3 | 1 | 0 | 29.3
Order new furniture elements |  | 4 | 0 | 1.5 | 0 | 0 | 0 | 0 | 5.5
Order library element |  | 4 | 0 | 1.5 | 0 | 0 | 0 | 0 | 5.5
Change the lights |  | 2 | 0 | 1 | 3 | 0.9 | 0 | 0.5 | 7.4
Upgrade electric installation |  | 0 | 0 | 1 | 6 | 1.8 | 0 | 0.5 | 9.3
Order carpets |  | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 4.5
Paint the walls |  | 1 | 1 | 1 | 4 | 1.2 | 0 | 0.5 | 8.7
Create some ceiling decoration |  | 3 | 1 | 1 | 4 | 1.2 | 0 | 0.5 | 10.7
Kitchen
Design how the kitchen will look like |  | 24 | 4 | 1 | 1 | 0.3 | 1 | 0 | 31.3
Order new furniture elements |  | 4 | 0 | 1.5 | 0 | 0 | 0 | 0 | 5.5
Order new tiles |  | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 2.5
Change the floor |  | 1 | 0 | 1 | 8 | 2.4 | 0 | 0.5 | 12.9
Order new fridge |  | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 2.5
Order new oven |  | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 2.5
Change the water pipes |  | 0 | 0 | 1 | 6 | 1.8 | 0 | 0.5 | 9.3
Upgrade the electric installation |  | 0 | 0 | 1 | 6 | 1.8 | 0 | 0.5 | 9.3
Paint the walls |  | 1 | 1 | 1 | 3 | 0.9 | 0 | 0.5 | 7.4
Change the lights |  | 2 | 0 | 1 | 3 | 0.9 | 0 | 0.5 | 7.4
Balconies
Order new tiles |  | 1 | 0 | 1.5 | 0 | 0 | 1 | 0 | 3.5
Paint the walls |  | 1 | 1 | 1 | 2 | 0.6 | 0 | 0.5 | 6.1
Order some balcony accessories |  | 2 | 0 | 1.5 | 0 | 0 | 0 | 0 | 3.5
Change the lights |  | 2 | 0 | 1.5 | 1 | 0.3 | 0 | 0.5 | 5.3
Order a storage furniture |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 4
TOTAL |  | 116 | 15 | 43.5 | 72 | 21.6 | 4 | 8 | 280.1